## Sheet1
Week
1
2
3
4
5

## Sheet2
Boost your projects with MS Project®
WEEK | CONTENT | ACTIVITY | NAME | TYPE | GRADING | START | END | REALIMENTACIÓN PROFESOR | Instructions
1 | Basic concepts and Introduction to MS Project, Schedule Management and Dependencies | Webinar Week 1 | Webinar | Individual | 0 | 2023-08-03 | 2023-08-03 | NA
|  | Guided Practice unit 1 - Apartment building (Not evaluated) | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-03 | 2023-08-03 | NA
|  | Guided Practice unit 1 Committee meeting (Not evaluated) | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-03 | 2023-08-03 | NA
|  | 01 Evaluated practice #1 (W1 Practice unit 1A and1B Calendars) | Evaluated practice | Individual | 20 | 2023-07-31 | 2023-08-07 | NA
2 | Resources and Cost Management | Webinar Week 2 | Webinar | Individual | 0 | 2023-08-10 | 2023-08-10 | NA
|  | Guided Practice unit 2 - Allocation of resources to project activities | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-10 | 2023-08-10 | NA
|  | 02 Evaluated practice unit #2 Evaluated Project unit 3B - RA Resources and costs | Evaluated practice | Individual | 20 | 2023-08-07 | 2023-08-14 | NA
3 | Project Monitoring, Tables and Reports in MS Project | Webinar Week 3 | Webinar | Individual | 0 | 2023-08-17 | 2023-08-17 | NA
|  | Guided Practice unit 3 - Set the status date and Actual status | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-17 | 2023-08-17 | NA
|  | 03 Evaluated Practice Unit 3 Baseline | Evaluated practice | Individual | 20 | 2023-08-15 | 2023-08-22 | NA
4 | Effort-Driven Scheduling, Tables and Filters customization | Webinar Week 4 | Webinar | Individual | 0 | 2023-08-10 | 2023-08-10 | NA
|  | Guided Practice unit 4 | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-10 | 2023-08-10
|  | 04A Evaluated practice unit #4 Restrictions | Evaluated practice | Individual | 10 | 2023-08-22 | 2023-08-29 | NA
|  | 04B Evaluated practice unit #4 Profiles and cost table | Evaluated practice | Individual | 10 | 2023-08-22 | 2023-08-29
5 | Earned Value | Webinar Week 5 | Webinar | Individual | 0 | 2023-08-17 | 2023-08-17 | NA
|  | Guided Practice unit 5 | Webinar ( Not Evaluated Practice) | Group | NA | 2023-08-17 | 2023-08-17
|  | Evaluated Practice Unit 5 Practice L2 Av Earned Value fixed cost-2021 (Evaluated) | Evaluated practice | Individual | 20 | 2023-08-30 | 2023-08-12 | NA
100
Formulas:
END = [START]+7
END = [START]