# Microsoft Project –  Basic Course PRACTICE

# Draft "  Committee meeting"

Requirements

Open the file drive 1-a 2021. Make  the  following modifications to the project:

It is about preparing a  committee meeting. The characteristics of the project are described below:

- Project:   Committee meeting

- Start Date: May 3  ,  2021

- Project Subject: Annual Report

- Administrator: Name of the Student.

# Enable project name  :

- Enable SUMMARY TASKS

- Enable the   PROJECT SUMMARY TASK  (task 0)

# Modifying  the initial   task list:

- Modify task 3  "Book conference center", to a duration of 3 days.

- Modify task 7 "Sort mailing list  ", to a duration of 1 day.

- Modify  task 8 "Prepare letter", to a duration of 3 days.

- Place task 12 "Send letter" as a milestone (without modifying its current  duration)

- Modify task  14 "Prepare menu with catering  company", to a duration of 1 week.

# Task Linking:

- Link all  tasks with an  end-to-start  dependency.

- Unlink   summary tasks  (select summary   tasks only    ).

- Link task 4, "Find speaker", with task 7, "Sort mailing list" with  a Start-Start dependency and a postponement time of 1 day.

- Link task 10, "Approve menu", with  task   14,   "Prepare menu with   catering  company".

Changes To the  project schedule:

- Specify a    1-day advance time  in the dependency between task  3 "Reserve Conference  Center"  and task 4, "Find Lecturer".

- Change   the dependency between  task   7, "Order  Sending List"   and task 8, "Prepare  Letter" to

"Beginning-Beginning"

- Change   the dependency between  task 14, "Prepare menu with catering",  and task 15, "  Prepare Committee Meeting Rooms", to "End -End"

- Specify a postponement time of 5 days between task 18, "Print schedule" and task 19, "Hold the meeting".

# Insert a repetitive task

- Executive  meetings are scheduled  on   Tuesdays of each week with the   company's chief executive  (2 hours) to present the follow-up of  the project. These meetings are held from the beginning until the project has ended.

---- End of Practice ----