## Hoja 1
Reserves
Code | Cause | Risk Description | Reference | WBS | Probability | Impact | Rank (P x I) | Response | Preventive Actions | Backup | Contingency Plan | Time (days) | Money ($) | Trigger | Responsible | Post-PlanProbability | Post-Plan Impact | Post-Plan Rank
RA003 | Lack of financing for the project | If there is a problem with the financing of the project, the project will not be able to start. | Project start-up | 2020-01-01 | 0.5 | 0.8 | 0.4 | Mitigate | Contemplate a capital and time reserve in both the contingency plan and the project schedule so that in the event of a delay due to lack of financing, the project can be started without generating a major impact in the long term. | [5 empty] | Gabriela Coronado | 0.3 | 0.1 | 0.03
RA003 | Lack of project financing | If there is a problem with project financing, the project will not be able to move forward. | Throughout the life cycle of the project | [5 empty] | Additional investors, borrowings. Having at least one alternative financing source or option.
RE001 | Climatic conditions | Adverse weather conditions resulting from severe storms during the construction of the terminal or roads may cause delays in the project schedule. | Rainy season activity dates | 2020-04-01 | 0.7 | 0.4 | 0.28 | Accept |  |  | 1. In the event that the rainy season starts before the completion of the project, the work schedule will be modified according to the weather and the conditions of the moment. 2. Record by means of evidence the delay due to adverse weather conditions to review with the client the possibility of providing a time extension. 3. Hire mobile awnings in specific areas. | 100 | $10.000 | Material losses due to natural disasters. | PM - Karla Leiton | 0.3 | 0.2 | 0.06
RE001 | Climatic and geographic conditions | Slope slides may occur in areas within or adjacent to the project site. | During an initial or design phase |  | 0.9 | 0.8 | 0.72 | Mitigate | Incorporation of slope stabilization and containment works. | Once designed and incorporated as part of the project deliverables, when the risk is re-evaluated, it is passively accepted. |  |  |  | Topographic review and soil studies. |  | 0.1 | 0.2 | 0.02
RE003 | Covid-19 disease | If a significant number of incapacities occur as a result of the contagion of project members, it may cause schedule delays. | Incapacity process and protocol for Covid-19 Pandemic | 1.2, 1.3, 1.4 y 1.5 | 0.7 | 0.4 | 0.28 | Mitigate | Have a previously defined work team to cover the functions and roles of the current team in case of possible COVID-19 contagions. Develop a draft contract with each of them so that in case of casualties, they can proceed immediately with the emergency team and avoid possible delays in the project schedule. | [5 empty] | Gabriela Coronado | 0.1 | 0.2 | 0.02
Project General Risk: High | [6 empty] | 0.42 | Total Amount of Contingency Reserves: |  |  |  | 111 days | 0 | Post-Plan Project General Risk: Low |  |  |  | 0.0325